# SCOPE OF WORK & PROPOSAL

Webb Advisory Group → Meridian Partners

Operational Due Diligence Assessment: Hartfield Precision Components

Prepared by: Marcus Webb | Date: June 3, 2026 | Valid through: June 30, 2026

## ENGAGEMENT OVERVIEW

Meridian Partners ("Client") has requested an operational due diligence assessment of Hartfield Precision Components ("Target") in connection with Meridian's proposed acquisition of a controlling interest at an estimated enterprise value of $62 million.

Webb Advisory Group ("Webb Advisory") proposes to conduct its standard management assessment and organizational health review as described below.

## SCOPE OF WORK

## Phase 1 — Document Review (Week 1–2)

Review of organizational charts, reporting structures, job descriptions for senior roles

Review of board meeting minutes (past 24 months)

Analysis of management team compensation and incentive structure

Review of any prior performance assessments or 360-degree feedback

Analysis of turnover data and exit interview themes where available

## Phase 2 — Management Interviews (Week 2–4)

Structured behavioral and situational interviews with:

CEO / President

CFO

COO / VP Operations

VP Sales / Commercial Lead

2–3 additional functional leaders identified during Phase 1

Each interview: 60–90 minutes. Protocol: Webb Advisory's proprietary framework (behavioral competencies + PE-readiness indicators).

## Phase 3 — Reference & Background Validation (Week 3–4)

Up to 8 reference calls (industry contacts, former colleagues, board members)

Public background research on key leaders

Comparison of stated credentials and track record against interview findings

## Phase 4 — Assessment & Report (Week 4–6)

Written assessment report (estimated 25–35 pages):

Executive Summary with overall risk rating

Individual leader profiles with competency ratings

Organizational health assessment

Integration risk flags (Red / Yellow / Green)

Recommended operating model adjustments post-close

Management presentation of findings (2 hours). Available for follow-up Q&A during the 30 days post-delivery.

## FEES & PAYMENT

Engagement fee: $31,000 (flat)

Based on: 4-person management team + 3 additional leaders, $62M EV deal size

Payment schedule:

$10,000 due upon execution of this agreement

$10,000 due upon delivery of Phase 2 (interview completion)

$11,000 due upon delivery of final report

Expenses: Travel costs billed at cost with receipts (estimated $1,500–$2,500).

Rush premium: If timeline is compressed to under 4 weeks at Meridian's request, an additional $4,000 applies.

## ASSUMPTIONS & EXCLUSIONS

Target management team will be available and cooperative with interview scheduling

Meridian will facilitate introductions and provide document access within 5 business days of signing

This proposal does not include financial or legal due diligence

Cybersecurity or IT infrastructure assessment is excluded unless separately scoped

## CONTACT

Marcus Webb | marcus@webbadvisory.com | (312) 555-0147 | webbadvisory.com